## Cover Page
The Cool Team
Team Members:
Marie Ella Cambay
Charles Dahan
Ilyess Diyane
Frederic Gagne
Pablo Hernandez
Quetin Malichecq-Laroche

## Product Back Log
Issue# | User Story | Associated Task | Associated Story Points | Priority Level | Risk Level | Members Resposible | Due Date
1 | When opening the website, the user is introduced with a login page | - Setup Website - Design and implement a login page - Configure website to display login page as default - Validate user input on the login display | 2 | HIGH | LOW | -Frederic - Marie - Pablo | 2026-02-06
2 | On the login page, the user has to have the option to either login, or create an account | - Provide an option to navigate to account creation - Design and implement an account registration page - Validate registration input | 5 | HIGH | MEDIUM | -Frederic - Marie - Pablo | 2026-02-06
3 | The user's information is saved when registered | - Define required user information - Create database to store information - Store user data upon registration - Prevent duplicate account - Confirm account creation | 3 | HIGH | MEDIUM | -Quentin | 2026-02-06
4 | The user is able to manage his profile, with information like diet preferences, and allergies | - Design interface for profile management - Display user's information and possibility to modify them - Store dietary preferences and allergy data - Validate the user's inputs | 4 | HIGH | MEDIUM | - Marie - Charles | 2026-02-06
5 | When loged in, the user is introduced to the menu page with a user friendly interface and the weekly meal schedule | - Design a user friendly main menu - Display buttons for features like profile management, calorie tracker, and recipe creator - Implement weekly meal schedule - Allow the user to remake the schedule - Ensure the schedule doesn't repeat meals - Ensure menu page is only accessible after login | 6 | HIGH | MEDIUM | - Charles - Quentin | 2026-03-27
6 | The user can access a page allowing to manage recipes (add, delete, modify, etc.) | - Design profile management interface - Design table that stores and displays the user's recipes - Implement system to add recipes - Implement system to remove recipes - Implement system to edit recipes | 5 | HIGH | LOW | - Frederic Gagne | 2026-02-27
7 | The user can look and filter through his recipes | - Design a recipe list layout that shows the key information of each recipes - Add search feature - Add filter option | 3 | MEDIUM | LOW | - Pablo | 2026-02-27
8 | The user can access a page where a calorie tracker advises him on his calorie consumption | - Design calorie tracker interface - Display total daily calories of the meals - Allow user's to add or remove daily calories from either eating food not in the schedule or exercise - Provide simple feedback and encouragements | 6 | MEDIUM | HIGH | - Charles - Quentin | 2026-04-14
9 | The user can give all ingridients he has, the app will return him with suggestions of recipes that are possible with those ingredients | - Design ingredient input interface - Allow user's to input valid ingredients - Use AI API to look for recipes based on ingredients and suggest them to the user - Allow users to add given recipes to their list | 7 | MEDIUM | HIGH | - Frederic Gagne - Pablo | 2026-04-14
10 | The user will enjoy an easy to learn user interface with fast response | - Create consistent and easy to navigate layout - Improve responsivness by reducing unecessary page reloads - Test the website with many different use cases to ensure bug free environment | 2 | LOW | LOW | - Marie - Charles | 2026-04-14
11 | The user can live comfortably knowing that his stored data is protected | - Ensure personnal information is stored correctly and securely - Restrict data access to people within the team only - Document which data is being used where and in what way (only necessary for user's personal information) | 3 | LOW | MEDIUM | - Quentin | 2026-04-14
Total story points |  |  | 46

## Contribution
|  | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | TOTAL
Marie Ella Cambay | Time Spent (hours) | 6 | 4 | 5 |  | 15
| Contributions | Debugged and resolved database insert errors (users now correctly save in phpMyAdmin) Improved UI/UX styling for the login and profile pages Added a consistent top header (logo + app name) across pages for a cleaner layout | Redesigned Recipes page layout Standardized styling across Add Recipe, Edit Recipe, and Recipes pages. Fixed Edit/Delete button alignment and styling | Designed the UI for the recipe creator page
Charles Dahan | Time Spent (hours) | 6 | 4 | 15 |  | 25
| Contributions | Helped Setup the Github page by creating the GitHub issues Display the user's dietary preferences on the profile page Store the allergies and dietary preferences data Link the allergies/preferences to the user | Setup the recipe display page Improved UI for the display page Helped with "Add recipe" | Added the weekly schedule to display the recipes chosen Added styling for the weekly schedule Added an error box if duplicate is added Helped with the recipe creation function
Frederic Gagne | Time Spent (hours) | 10 | 10 | 20 |  | 40
| Contributions | Created the GitHub, and helped fill out the product backlog. Setup the login and registration page. Setup the main menu and the profile page. Added the allergies in the profile page. | Added the recipe tables in the database Setup the add recipe function Helped with the recipe display Helped with the edit recipes Helped with the delete recipes | Added the recipe creation function Added the styling to the calorie tracker page and debugged it Helped with the main menu schedule Helped with the calorie tracker Refactored code to have functions instead of duplicate code
Pablo Hernandez | Time Spent (hours) | 2 | 4 | 5 |  | 11
| Contributions | Helped set up Github files, and fill product backlog. Kept record of meeting minutes | Setup the recipe filtering, sorting and searching | Helped with claorie tracker and profile
Quetin Malichecq-Laroche | Time Spent (hours) | 5 | 4 | 12 |  | 21
| Contributions | found and setup the database and website host setup and debugged connectivity between website and database | Created acceptance tests for sprint 1 user stories Setup continuous integration pipeline | Updated Continuous Integration pipeline to utilize unit tests Created unit tests for sprint 1 and 2 features
Ilyess Diyane | Time Spent (hours) | 0 | 4 | 5 |  | 9
| Contributions | Joined the team a bit late and was overseas. | Setup the edit recipe function, and the remove recipe function. | Wrote some Acceptance Tests for some User Stories by testing the platform. With help, did the calorie tracker